| THEME | H2020-ICT-2016-2017 | PILLAR: | Industrial Leadership |
| --- | --- | --- | --- |
| ACTION TYPE / BUDGET | RIA: Research and Innovation action. Recommended budget: 2-4 mil Euro |  |  |
| TOPIC | ICT-20-2017: Tools for smart digital content in the creative industries |  |  |
| ACRONYM / TITLE | ACRONYM: Working Title |  |  |

# WBS EXAMPLE

- WP1: Project Management [LEAD]

  - Strategic Management, Coordination & Financial Administration (LEAD)

D1.1 – Self-assessment plan [M6 v1, M18 Update, Report]

  - Project Management Office (LEAD)

D1.2 – Interim management report [M6, M18, M30, Report]

D1.3 – Periodic report [M12 Y1, M24 Y2, M36 Y3, Report}

- WP2: Requirements Analysis and Content Management [LEAD]

  - User and Functional/Non-functional Requirements Analysis (LEAD)

D2.1 – User and functional/non-functional requirements [M6 v1, M18 Update, Report].

  - Technical specifications (LEAD)

D2.2 – Technical specification [M6, M18, M30, Report]

  - Advanced Market Research: Analysis of users preferences and hidden groups (LEAD)

D.2.3- Advanced Market Research: Analysis of users’ preferences and hidden groups [M10, M20 Update, Report].

  - Case Study Definitions and Study of Digital Research Methodologies (LEAD)

D2.4 – Case studies and digital research methodologies [M12 Y1, M24 Y2, M36 Y3, Report]

- WP3: …. [LEAD]

- WP4: …. [LEAD]

- WP5: …. [LEAD]

- WPx

- WPx: Innovation Management, Dissemination and Exploitation

  - Awareness creation strategy, plan and implementation (LEAD)

D7.1 – Awareness Creation Plan [M5, M15, M25, Report]

  - Dissemination and Stakeholder Engagement (LEAD)

D7.21 – Dissemination Plan [M5, M15, M25, Report]

D7.22 –Dissemination Actions Report [M35, Report]

  - Data Management & IPR (LEAD)

D7.31 – Data Management & IPR Plan [M8 v1, M18 v2, M36 v3, Report]

  - Knowledge Transfer & Exploitation (LEAD)

D7.4- Knowledge Transfer & Exploitation [M12 v1, M36 v2, Report]

  - Business Models and Commercialization (LEAD)

D7.5 –Business & Commercialization Plan [M8 v1, M18 v2, M36 v3, Report]