## PARTNERS
MOON PROJECT
CONSORTIUM PARTNERS
# | Role | Name | Short Name | Country | Type | Contacts | E-mail addresses | PIC
1 | COO | COORDINATOR | COOR
2 | PAR | PARTNER 1 | PAR1
3 | PAR | PARTNER 2 | PAR2
4 | PAR | PARTNER 3 | PAR3
5 | PAR | PARTNER 4 | PAR4
6 | PAR | PARTNER 5 | PAR5
7 |  | PARTNER 6

## WPs
MOON PROJECT
WORK PACKAGES
# | Name | Description
1 | PROJECT MANAGEMENT | Project Coordination
2
3
4
5
6

## WBS
MOON PROJECT
|  |  | Work Breakdown Structure & Person Months / Partner | [46 empty] | 0
L | WBS |  | CODE | ACTIVITIES / TASKS TITLE | LEAD | COOR | PAR1 | PAR2 | PAR3 | PAR4 | PAR5 | ΤOTAL | P1 | P2 | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
[15 empty] | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
1 | 1 |  | WP1 | PROJECT MANAGEMENT
2 | 1.1 | WP1 | T1.1 | Consortium Planning / Action Plan | [7 empty] | 0 | 0 |  | YEAR 1 M1: D1.1
2 | 1.2 | WP1 | T1.2 | Collaboration Platform | [7 empty] | 0 | 0 |  | YEAR 1 M2: D1.2; YEAR 1 M3: 📍MS1
2 | 1.3 | WP1 | T1.3 | Monitoring, Reporting & Risk Management | [7 empty] | 0 | 2 | -2 | YEAR 1 M7: 📔 PROGRESS REPORT; YEAR 2 M13: 📔 PR; YEAR 2 M19: 📔 PR; YEAR 3 M25: 📔 PR; YEAR 3 M31: 📔 PR
2 | 1.4 | WP1 | T1.4 | Quality Control | [7 empty] | 0 | 0 |  | YEAR 1 M1: D1.4
2 | 1.5 | WP1 | T1.5 | Meetings & Communication | [7 empty] | 0 | 0 | 0 | YEAR 1 M1: D1.5
1 | 2 |  | WP2 | 0 | bar: YEAR 1 M4 to YEAR 1 M12; YEAR 3 M32 to YEAR 3 M34
2 | 2.1 | WP2 | Τ2.1 | [8 empty] | 0 | 0 | bar: YEAR 1 M3 to YEAR 1 M12; YEAR 3 M32 to YEAR 3 M34
2 | 2.2 | WP2 | Τ2.2 | [8 empty] | 0 | 0 | bar: YEAR 1 M5 to YEAR 1 M12; YEAR 3 M32 to YEAR 3 M34
2 | 2.3 | WP2 | Τ2.3 | [8 empty] | 0 | 0 | bar: YEAR 1 M8 to YEAR 1 M11; YEAR 3 M32 to YEAR 3 M34
1 | 3 |  | WP3 | 0 | bar: YEAR 3 M32 to YEAR 3 M34
2 | 3.1 | WP3 | T.3.1 | [8 empty] | 0 | 0 | bar: YEAR 1 M7 to YEAR 2 M14; YEAR 3 M32 to YEAR 3 M34
2 | 3.2 | WP3 | T.3.2 | [8 empty] | 0 | 0 | 0 | bar: YEAR 1 M8 to YEAR 2 M16; YEAR 3 M26 to YEAR 3 M30; YEAR 3 M32 to YEAR 3 M34
2 | 3.3 | WP3 | T.3.3 | [8 empty] | 0 | 0 | bar: YEAR 2 M14 to YEAR 2 M18; YEAR 3 M32 to YEAR 3 M34
2 | 3.4 | WP3 | T.3.4 | [8 empty] | 0 | 0 | 0 | YEAR 3 M34: D3.4
1 | 4 |  | WP4 | 0 | bar: YEAR 3 M32 to YEAR 3 M34
2 | 4.1 | WP4 | T4.1 | [8 empty] | 0 | 0 |  | YEAR 2 M15: D4.1
2 | 4.2 | WP4 | T4.2 | [8 empty] | 0 | 0 |  | YEAR 2 M18: D4.2, D4.3; YEAR 2 M19: 📍MS4
2 | 4.3 | WP4 | T4.3 | [8 empty] | 0 | 0 | 0 | YEAR 2 M21: D4.4; YEAR 2 M22: 📍MS5 (Μ21)
1 | 5 |  | WP5 | 0 | bar: YEAR 3 M32 to YEAR 3 M34
2 | 5.1 | WP5 | T5.1 | [8 empty] | 0 |  | 0 | YEAR 2 M24: D5.1; YEAR 3 M25: 📍MS6
2 | 5.2 | WP5 | T5.2 | [8 empty] | 0 |  | 0 | YEAR 3 M32: D5.2
2 | 5.3 | WP5 | T5.3 | [8 empty] | 0 |  | 0 | YEAR 3 M33: D5.3
2 | 5.4 | WP5 | T5.4 | [8 empty] | 0 |  | 0 | YEAR 3 M34: D5.4
1 | 6 |  | WP6 | 0 | bar: YEAR 3 M32 to YEAR 3 M34
2 | 6.1 | WP6 | T6.1 | [8 empty] | 0 | 0 | 0 | YEAR 1 M6: D6.1; YEAR 1 M7: 📍MS7
2 | 6.2 | WP6 | T6.2 | [8 empty] | 0 | 0 | 0 | YEAR 3 M34: D6.2
2 | 6.3 | WP6 | T6.3 | [8 empty] | 0 | 0 | 0 | YEAR 3 M34: D6.3
2 | 6.4 | WP6 | T6.4 | [8 empty] | 0 | 0 | 0 | bar: YEAR 1 M1 to YEAR 1 M2; YEAR 2 M15 to YEAR 2 M18; YEAR 2 M20 to YEAR 3 M28; YEAR 3 M32 to YEAR 3 M34
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -2

## PMs
MOON PROJECT
L | WBS | # | PARTNER | SHORT NAME | TOTAL | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | P1 | P2
2 | 1.1 | 1 | COORDINATOR | COOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  | 2 | PARTNER 1 | PAR1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  | 3 | PARTNER 2 | PAR2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  | 4 | PARTNER 3 | PAR3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  | 5 | PARTNER 4 | PAR4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | 1.1 | 6 | PARTNER 5 | PAR5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
|  |  | PERIOD 1 | (M1-M18) | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  |  | PERIOD 2 | M19-M36) | -2 | -2 | 0 | 0 | 0 | 0 | 0
|  |  | PROJECTED EFFORT IN P1 |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[5 empty] | PROJECT MANAGEMENT IN TOTAL PROJECT | #DIV/0!
[6 empty] | SCK | AUTH | PROG | ASDK | TUVA | LWCY
[5 empty] | WP1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP2 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP3 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP4 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP5 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP6 | 0 | 0 | 0 | 0 | 0 | 0
INVERTED TABLE

## BUDGET
PROJECT BUDGET PER PARTNER
Columns B:Subcontracting & C:Support to Third Parties hidden since = 0
[8 empty] | Overheads: | 7%
# | NAME | A. PERSONNEL | B. SUBCONT | C. THIRD PARTIES | D1. TRAVEL | D2. EQUIP | D3. OTHER | D. TOTAL OTHER | F. INDIRECT (7%) | TOTAL | MAX REIMB RATE | BUDGET DISTRIBUTION | GRANT
1 | COORDINATOR | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
2 | PARTNER 1 | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
3 | PARTNER 2 | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
4 | PARTNER 3 | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
5 | PARTNER 4 | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
6 | PARTNER 5 | [6 empty] | 0 | 0 | 0 | 80% | #DIV/0! | 0
[10 empty] | 0 |  |  | 0

## Lists (hidden)
LIST OF PERSONNEL
Project Managers
Senior Experts
Junior Experts
Trainers
Technical
Administrative